Department of Computer Science

Request for Tenders No. 2026-CSE5IDP-S2-W

LEARNING JOURNEY ASSISTANT

| Lodgement Place: | LMS Subject Shell Tender Box Attention: Project Owner RFT No. 2026-CSE5IDP-S2-W Department of Computer Science, La Trobe University. |
| --- | --- |
| Submission Date | 23/08/2026 |

| Tenderer details |  |  |  | ABN: | Student project |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | ACN: | Student project |  |  |  |
| Tenderer’s legal name: |  | Learning Journey Assistant – Group 3 CSE5IDP |  |  |  |  |  |  |
| Postal Address: |  | La Trobe University / Online cohort |  |  |  |  |  |  |
| Street Address: |  | N/A - university student project |  |  |  |  |  |  |
| City/Town: |  | Bundoora | State: | VIC |  |  | P/code: | 3086 |
| Authorised contact: |  | Allan Campton |  |  |  |  |  |  |
| Email Address: |  | 21206266@students.latrobe.edu.au | Phone: | N/A |  |  | Fax: | N/A |

1 Project Summary

| Element | Project Summary |
| --- | --- |
| Purpose | Develop an AI-powered Learning Journey Assistant that converts Moodle assessment results, rubrics, feedback and learning outcomes into a personalised view of student mastery, strengths, learning gaps and next study actions. |
| Business Context | La Trobe already holds rich learning data in Moodle, but students do not have a single structured mechanism that turns marks and feedback into actionable, personalised learning guidance. The project addresses this gap while preserving academic governance and privacy. |
| Objective | Deliver a Minimum viable product (MVP) that demonstrates an end-to-end flow from synthetic Moodle data through extraction, competency, SILO mapping and gap detection to a student dashboard, followed by grounded learning recommendations and, adaptive quizzes. |
| Complexity | Moderate-to-high complexity: Moodle 5.2 integration, rubric data extraction limitations, cross-subject competency mapping, explainable gap calculations, AI grounding, privacy/security controls, dashboard integration, testing and five-person Agile delivery. |
| Feasibility Statement | Feasible within the semester as the team prioritising a thin vertical slice. The repository already contains a working Dockerised Moodle environment, API/extraction spike and read-only SQL groundwork; the main remaining work is integration, the competency/gap engine, dashboard, AI features and validation. |
| Recommendations | Prioritising the walking skeleton first; remain local-first; using synthetic data and least-privilege access; confirming gap thresholds and Moodle outcome mechanism early with the project owner; require PR/testing evidence; descope quizzes before the core dashboard and gap-detection capability if time becomes constrained. |

2. Business Assessment

The business case is to improve how existing Moodle information is transformed into practical learning support rather than replace Moodle, teaching staff or formal assessment processes.

| Area | Assessment |
| --- | --- |
| Situation Assessment | Students receive marks, rubric decisions and feedback across separate Moodle activities, but the information is fragmented and difficult to interpret longitudinally. Moodle also contains learning outcomes/competencies that can support a more structured mastery model. |
| Problem Statement | Students lack a reliable way to understand what they have mastered, where knowledge gaps persist, why those gaps matter and what they should study next. Existing feedback is therefore underused and does not automatically become an individual improvement plan. |
| Business Need | Provide a practical, transparent and privacy-conscious learning-support layer that increases feedback utilisation, self-regulated learning and visibility of progress without changing official grades. |

Options Consideration

| Option | Benefits | Limitations | Assessment |
| --- | --- | --- | --- |
| 1. Manual reports | Low technical complexity and low cost. | Static, labour intensive, weak personalisation and poor longitudinal capability. | Not preferred |
| 2. Standalone LJA using Moodle APIs + read-only SQL + dashboard | Balances integration, control, privacy, explainability and speed; supports a full MVP. | Requires careful mapping and an additional path for rubric fills. | Recommended |
| 3. Full custom Moodle plugin | Deep native integration and cleaner access to Moodle-specific data. | Higher build, testing and maintenance effort within one semester. | Stretch option |
| 4. Cloud-first external AI solution | Rapid access to scalable AI services. | Higher governance, data-transfer, cost and privacy risk; unnecessary for the MVP. | Defer |

3. Project Scope

| Scope Area | Definition |
| --- | --- |
| In Scope | Securing Moodle development integration; synthetic students; assessment/rubric/feedback extraction; competency/SILO mapping; mastery and gap detection; dashboard; progress view; recommended resources; personalised study guidance; adaptive quiz capability; testing, security, documentation and handover. |
| Out of Scope | Changing official grades; replacing academic judgement; use of identifiable real student data in the MVP; university-wide production rollout; mandatory cloud migration; predictive academic-risk analytics and employability-framework integration unless treated as stretch work. |
| Assumptions | The project owner will provide or approve representative subject structures/course backups and SILOs; synthetic student records are acceptable for development; team members have access to Jira, GitHub and the local development stack. |
| Constraints | University privacy and security requirements; Moodle API coverage gaps for rubric fills; outputs must be grounded in structured subject data; finite semester schedule; six-person team availability; external/project-owner response times. |
| Scope of Work | Set up and seed Moodle; extract and normalise learning data; map criteria to outcomes; calculate mastery/gaps; implement dashboard; generate grounded study support; add adaptive quiz where feasible; execute QA/security checks; prepare handover and demonstration artefacts. |
| Implementation Strategy | Six Agile sprints using a thin vertical-slice approach. Building one-student/one-subject walking skeleton first, then expand. Use Dockerised Moodle, Python, read-only PostgreSQL access where required, CI/PR review, acceptance-criteria-driven testing and incremental project-owner demonstrations. |
| Governance / Team Agreement | Rotating Scrum Master; Jira as work/evidence source; GitHub branch and pull-request workflow; Definition of Done requires acceptance criteria, checks, documentation and evidence; at least one peer reviewer for merge-ready changes; decisions recorded in Jira/meeting notes. |

Key Risks and Controls

| Risk | Level | Primary Control |
| --- | --- | --- |
| Rubric fills not available through standard Moodle Web Services | High | Use least-privilege read-only SQL for the MVP; consider a custom Moodle web-service plugin as stretch work. |
| Project-owner dataset decision delays | High | Use synthetic data and worked examples so development continues; record decisions needed and raise them early. |
| LLM hallucination or unsupported recommendations | Very High | Ground every AI call in structured marks/rubric/gap data; prohibit invented marks/feedback; validate outputs with test cases and human review. |
| Privacy or credential exposure | Very High | No real student data; least-privilege tokens/roles; repository security checks. |
| Scope creep / late feature requests | High | Must-have/nice-to-have prioritisation and agreed descope order; protect dashboard + gap-detection core. |
| Single-person technical dependency | Medium | Peer review, shared documentation, pairing and knowledge transfer across the six-person team. |
| Integration defects | High | Walking skeleton early, integration testing each sprint and acceptance evidence before Done. |
| Schedule underestimation | High | Track velocity/burndown, re-estimate regularly and move non-critical features to later sprints. |

4 Project Evaluation Matrix

| Evaluation Area | Target / Success Metric | Evidence |
| --- | --- | --- |
| End-to-end MVP | At least one synthetic student and one subject flow from Moodle data to mapped gap results and dashboard without manual re-entry. | Live demonstration + integration test |
| Data extraction | Required course, grade, feedback and rubric fields are extracted consistently; Moodle source tables are never directly modified. | Extraction logs + reviewed SQL/API tests |
| Criterion-to-SILO mapping | 100% of rubric criteria used in the demo are mapped to a SILO or explicitly flagged as unmapped for review. | Mapping report |
| Gap-detection correctness | All agreed deterministic validation cases pass and calculated mastery/gap classifications match hand-checked expected results. | Unit tests + validation worksheet |
| Dashboard completeness | Current understanding, strengths, gaps and progress views render correctly for all demo subjects; recommended next actions are visible. | UAT checklist +screenshots |
| AI grounding | No invented marks or marker feedback in the validation set; each generated recommendation/quiz is traceable to supplied gap/outcome data. | Prompt/output audit samples |
| Quality assurance | All critical acceptance tests pass; core mapping/gap logic targets at least 80% unit-test coverage. | CI/test report |
| Security & privacy | 0 real student records; 0 committed secrets; least-privilege access; no unresolved high-severity findings before handover. | Security checklist + repository scan |
| Performance | Normal local dashboard interactions respond within approximately 2 seconds, excluding optional external LLM generation time. | Performance test log |
| Usability | Project-owner/team UAT completes all critical student tasks without a blocker and records improvement actions. | UAT / sprint-review notes |
| Process & maintainability | Every completed story has acceptance evidence; merge-ready code is peer reviewed; setup and handover instructions reproduce the environment. | Jira + PR history + README verification |

Key Deliverables

| Deliverable | Target Sprint / Stage | Definition of Completion |
| --- | --- | --- |
| Local Moodle + synthetic data environment | Sprint 3 | Repeatable Dockerised setup with representative courses/students and documented start/seed steps. |
| Moodle extraction + competency mapping layer | Sprints 3-4 | API/read-only SQL extraction works and criteria can be mapped to SILOs. |
| Gap-detection engine | Sprint 4 | Per-outcome mastery and isolated/persistent gaps calculated and validated. |
| Visual Mastery Dashboard | Sprints 4-5 | Student can view mastery, strengths, gaps, progress and recommended next actions. |
| Grounded personalised learning support | Sprints 4-5 | Learning plan/study recommendations are generated from structured gap data and pass grounding checks. |
| Adaptive quiz | Sprint 5-6 | Quiz items align to identified gaps and provide feedback; first descope candidate if schedule slips. |
| QA, security, documentation and final handover | Sprints 5-6 | Acceptance testing, security evidence, setup documentation, final demonstration and handover package complete. |

5. Tender Evaluation Criteria and Requirements

The following requirements will be used to evaluate the proposed Learning Journey Assistant MVP.

| No | Requirements | Importance |
| --- | --- | --- |
| 1 | Secure end-to-end Moodle data extraction, competency/SILO mapping and learning-gap analysis. | Very High |
| 2 | Student dashboard and AI outputs must be grounded, explainable and useful for learning support. | Very High |
| 3 | Privacy-compliant MVP using synthetic data, documented testing and reproducible handover. | Mandatory / Yes |

Evaluating the project against the following weighted criteria:

| No | Criteria | Weighting |
| --- | --- | --- |

| 1 | Functional completeness: Moodle-to-dashboard workflow, gap detection and required student views. | 30% |
| --- | --- | --- |
| 2 | Accuracy and AI grounding: correct mapping/calculation, relevant recommendations and no invented academic data. | 25% |
| 3 | Security, privacy and quality: least privilege, synthetic data, testing, CI and risk controls. | 25% |
| 4 | Usability, maintainability and handover quality: clear UX, documentation and reproducibility. | 20% |

6.  Price and Budget

| Core software: Moodle, Docker, PostgreSQL, Python and open-source development tools. | $0 / Freeware |
| --- | --- |
| Development hardware and internet access. | In-kind (team resources) |
| Optional external LLM API for higher-quality generation; local model remains available. | Usage-based; cap TBC |
| Cloud production hosting. | $0 for MVP - deferred |

7 Constraints, Risks and Limitations

| 1 | Moodle Web Services do not expose rubric fills; use read-only SQL now and custom service/plugin only if capacity permits. | High |
| --- | --- | --- |
| 2 | Dataset, threshold and Moodle outcome-mechanism decisions depend on project-owner input; continue with synthetic data while waiting. | High |
| 3 | AI hallucination/privacy risk; ground prompts in structured data, prohibit invented marks/feedback and keep identifiable data out of the MVP. | Very High |
| 4 | Schedule, integration and scope-creep risk; protect the walking skeleton, use peer review/testing and descope non-core AI features first. | High |

8 Deliverables and Anticipated Hours and Timelines

| Deliverables | Anticipated team-hours | Delivered by |
| --- | --- | --- |
| Dockerised Moodle + synthetic sample data | 35 | Sprint 3 |
| Extraction + competency/SILO mapping |  |  |
| Gap-detection engine + validation |  |  |
| Visual Mastery Dashboard |  |  |
| Grounded learning plan + adaptive quiz capability |  |  |
| QA, security, documentation, demo and handover |  |  |

9 Statement of Work

Description of work

Design, implement, test and document a Learning Journey Assistant MVP. The team will configure a synthetic Moodle environment; extract assessment, rubric and feedback data; map criteria to subject intended learning outcomes; calculate mastery and learning gaps; present those results through a student dashboard; and add grounded personalised study recommendations and adaptive quiz functionality where schedule permits. Work will be delivered iteratively through six Agile sprints using Jira, GitHub branches, pull-request review, CI/testing evidence and project-owner sprint reviews. The solution will not modify official grades or use identifiable real student data.

10. Team Capabilities

| Team Member (Name) | Primary capability / contribution |
| --- | --- |
| Member 1 - insert name |  |
| Member 2 - insert name |  |
| Member 3 - insert name |  |
| Member 4 - insert name |  |
| Member 5 - insert name |  |